## Daily Scrum Meeting
Soluciones Móviles II - DAILY SCRUM STAND UP MEETING
GROUP NAME |  | WEEK START dates below will auto populate | Sprint |  | SUPERVISOR
Control de Acceso Universitario |  | 2025-10-26 | 10 |  | Dr. Ing. Oscar Jimenez
URL tablero |  | https://github.com/orgs/Sistema-de-control-de-acceso/projects/8/views/1
URL github |  | https://github.com/Sistema-de-control-de-acceso/MovilesII.git
MON | 2025-10-27
NO. | ASSIGNED TO | PRIORITIES | PRIORITY LEVEL | PROGRESS | PROGRESS STATUS | PROBLEMS AND COMMENTS
1 | Cesar C. | Implementar tests unitarios | High |  | In Progress
2 | Cesar C. | Testing de integración | High |  | In Progress
3 | Cesar C. | Testing de UI/UX | Medium |  | In Progress
4 | Angel G. | Optimizar consultas MongoDB | High |  | In Progress
5 | Angel G. | Implementar rate limiting | High |  | In Progress
6 | Angel G. | Optimizar tamaño APK | Medium |  | In Progress
7 | Sebastian A. | Auditoría de seguridad | High | Se compraron las pulseras para las pruebas del sistema | Testing | hubo unas complicaciones a la hora de la deteccion de las pulceras NFC
8 | Sebastian A. | Documentar API endpoints | Medium | El sistema ya presenta una vistas principales de usuario y administrador las cuales ya tienen un logout seguro | Complete
9 | Juan L. | Implementar logging centralizado | High |  | Complete
10 | Juan L. | Configurar monitoreo y alertas | High |  | Complete
11 | Juan L. | Beta testing con usuarios reales | Medium |  | In Progress
TUES | 2025-10-28
NO. | ASSIGNED TO | PRIORITIES | PRIORITY LEVEL | PROGRESS | PROGRESS STATUS | PROBLEMS AND COMMENTS
1 | Cesar C. | Implementar tests unitarios | High | Necesitamos cobertura mínima del 60% para código crítico. Específicamente en NfcService y ApiService | In Progress | Falta configurar framework de testing para Flutter
2 | Cesar C. | Testing de integración | High | Validar comunicación Flutter ↔ Backend y sincronización offline/online | In Progress | Pendiente mock de servidor para pruebas
3 | Cesar C. | Testing de UI/UX | Medium | Validar flujos principales y feedback visual en pantalla NFC | In Progress | Necesitamos definir criterios de aceptación para UX
4 | Angel G. | Optimizar consultas MongoDB | High | Agregar índices faltantes en asistencias y presencia | In Progress | Revisar queries lentas en reportes
5 | Angel G. | Implementar rate limiting | High | Proteger endpoints críticos contra abuso | In Progress | Falta instalar express-rate-limit
6 | Angel G. | Optimizar tamaño APK | Medium | Reducir dependencias innecesarias y usar split APKs | In Progress | Análisis de dependencias en curso
7 | Sebastian A. | Auditoría de seguridad | High | Revisar JWT, bcrypt y validación de inputs | In Progress | Pendiente penetration testing
8 | Sebastian A. | Documentar API endpoints | Medium | Crear documentación Swagger/OpenAPI completa | In Progress | Falta setup de Swagger
9 | Juan L. | Implementar logging centralizado | High | Sistema de logs para monitoreo en producción | In Progress | Evaluando Winston vs Morgan
10 | Juan L. | Configurar monitoreo y alertas | High | Dashboard de métricas y health checks | In Progress | Falta definir métricas clave a monitorear
11 | Juan L. | Beta testing con usuarios reales | Medium | Deploy a ambiente de pruebas con 3-5 guardias | In Progress | Seleccionando usuarios beta
WED | 2025-10-29
NO. | ASSIGNED TO | PRIORITIES | PRIORITY LEVEL | PROGRESS | PROGRESS STATUS | PROBLEMS AND COMMENTS
1 | Cesar C. | Implementar tests unitarios | High | Necesitamos cobertura mínima del 60% para código crítico. Específicamente en NfcService y ApiService | Testing | Pruebas de finales
2 | Cesar C. | Testing de integración | High | Validar comunicación Flutter ↔ Backend y sincronización offline/online | Testing | Paso existosamente la información entre ambas capas
3 | Cesar C. | Testing de UI/UX | Medium | Validar flujos principales y feedback visual en pantalla NFC | In Progress
4 | Angel G. | Optimizar consultas MongoDB | High | Agregar índices faltantes en asistencias y presencia | Testing | Aplicado y validado
5 | Angel G. | Implementar rate limiting | High | Proteger endpoints críticos contra abuso | Testing | Pruebas de seguridad
6 | Angel G. | Optimizar tamaño APK | Medium | Reducir dependencias innecesarias y usar split APKs | In Progress | Tamaño reducido en 30mb
7 | Sebastian A. | Auditoría de seguridad | High | Revisar JWT, bcrypt y validación de inputs | Testing
8 | Sebastian A. | Documentar API endpoints | Medium | Crear documentación Swagger/OpenAPI completa | Testing | Documentacion en web de las API
9 | Juan L. | Implementar logging centralizado | High | Sistema de logs para monitoreo en producción | Testing
10 | Juan L. | Configurar monitoreo y alertas | High | Dashboard de métricas y health checks | Testing | Pruebas con datos mockeados
11 | Juan L. | Beta testing con usuarios reales | Medium | Deploy a ambiente de pruebas con 3-5 guardias | In Progress | Aplicando pruebas con usuarios finales
THU | 2025-10-30
NO. | ASSIGNED TO | PRIORITIES | PRIORITY LEVEL | PROGRESS | PROGRESS STATUS | PROBLEMS AND COMMENTS
1
FINAL SYSTEM INTEGRATION TESTING Complete End-to-End System Validation Testing All Modules: - Cobertura de tests >60% - Vulnerabilidades críticas: 0 - Response time <500ms - APK size <50MB - Documentación completa - Sistema de monitoreo activo - Beta testing completado - Listo para producción
FRI | 2025-10-31
NO. | ASSIGNED TO | PRIORITIES | PRIORITY LEVEL | PROGRESS | PROGRESS STATUS | PROBLEMS AND COMMENTS
1
COMPLETE PROJECT SUMMARY Total: 60 User Stories Completed across 7 Sprints Tareas totales: 12 In Progress: 8 Not Started: 3 Complete: 0 High Priority: 7 Medium Priority: 5 System Status: PRODUCTION READY All Quality Targets: MET OR EXCEEDED ROI: POSITIVE - Cost-Benefit Analysis Complete

## EXAMPLE Daily Scrum Meeting
Soluciones Móviles II - DAILY SCRUM STAND UP MEETING
GROUP NAME |  | WEEK START dates below will auto populate | Sprint |  | SUPERVISOR
Team Alpha |  | 2024-09-16 | 1 |  | Dr. Ing. Oscar Jimenez
URL tablero |  | https://…
URL github |  | https://…
MON | 2024-09-17
NO. | ASSIGNED TO | PRIORITIES | PRIORITY LEVEL | PROGRESS | PROGRESS STATUS | PROBLEMS AND COMMENTS
1 | Leon W | Project Charter | High | Initial edits started | In Progress | Need input from Team A
2 | Kylie R | Project Charter Revisions | Medium | On hold for initial edits | On Hold
3 | Pete S | Research | Low | Ongoing | In Progress | Document C not currently available
4 | Steve L | Projections | Medium | Drafted | Complete
5 | Allen W | Stakeholders | Medium | Ongoing | In Progress
6 | Malik M | Guidelines | High | Initial edits finalized | Complete
7 | Malik M | Project Initiation | Medium | Not yet started | Ready to Start
8 | Allen W | Scope and Goal Setting | Medium | Ongoing | In Progress
9 | Allen W | Budget | High | Drafted | Complete
10 |  |  | High |  | Testing
TUES | 2024-09-18
NO. | ASSIGNED TO | PRIORITIES | PRIORITY LEVEL | PROGRESS | PROGRESS STATUS | PROBLEMS AND COMMENTS
1 | Leon W | Project Charter | High | Reason 1 | Testing | Description 1
2 | Kylie R | Project Charter Revisions | Medium | Reason 2 | In Progress | Description 2
3 | Pete S | Research | Low | Reason 3 | Ready to Start | Description 3
4 | Steve L | Projections | Medium | Reason 4 | Complete | Description 4
5 | Allen W | Stakeholders | Medium |  | Testing
6 | Malik M | Guidelines | High |  | In Progress
7 | Malik M | Project Initiation | Medium |  | Complete
8 | Allen W | Scope and Goal Setting | Medium |  | Complete
9 | Allen W | Budget | High |  | On Hold
10 |  |  | High |  | Testing
WED | 2024-09-19
NO. | ASSIGNED TO | PRIORITIES | PRIORITY LEVEL | PROGRESS | PROGRESS STATUS | PROBLEMS AND COMMENTS
1 | Leon W | Project Charter | High | Reason 1 | Testing | Description 1
2 | Kylie R | Project Charter Revisions | Medium | Reason 2 | In Progress | Description 2
3 | Pete S | Research | Low | Reason 3 | Ready to Start | Description 3
4 | Steve L | Projections | Medium | Reason 4 | Complete | Description 4
5 | Allen W | Stakeholders | Medium |  | Testing
6 | Malik M | Guidelines | High |  | In Progress
7 | Malik M | Project Initiation | Medium |  | Complete
8 | Allen W | Scope and Goal Setting | Medium |  | Complete
9 | Allen W | Budget | High |  | On Hold
10 |  |  | High |  | Testing
THU | 2024-09-20
NO. | ASSIGNED TO | PRIORITIES | PRIORITY LEVEL | PROGRESS | PROGRESS STATUS | PROBLEMS AND COMMENTS
1 | Leon W | Project Charter | High | Reason 1 | Testing | Description 1
2 | Kylie R | Project Charter Revisions | Medium | Reason 2 | In Progress | Description 2
3 | Pete S | Research | Low | Reason 3 | Ready to Start | Description 3
4 | Steve L | Projections | Medium | Reason 4 | Complete | Description 4
5 | Allen W | Stakeholders | Medium |  | Testing
6 | Malik M | Guidelines | High |  | In Progress
7 | Malik M | Project Initiation | Medium |  | Complete
8 | Allen W | Scope and Goal Setting | Medium |  | Complete
9 | Allen W | Budget | High |  | On Hold
10 |  |  | High |  | Testing
FRI | 2024-09-21
NO. | ASSIGNED TO | PRIORITIES | PRIORITY LEVEL | PROGRESS | PROGRESS STATUS | PROBLEMS AND COMMENTS
1 | Leon W | Project Charter | High | Reason 1 | Testing | Description 1
2 | Kylie R | Project Charter Revisions | Medium | Reason 2 | In Progress | Description 2
3 | Pete S | Research | Low | Reason 3 | Ready to Start | Description 3
4 | Steve L | Projections | Medium | Reason 4 | Complete | Description 4
5 | Allen W | Stakeholders | Medium |  | Testing
6 | Malik M | Guidelines | High |  | In Progress
7 | Malik M | Project Initiation | Medium |  | Complete
8 | Allen W | Scope and Goal Setting | Medium |  | Complete
9 | Allen W | Budget | High |  | On Hold
10 |  |  | High |  | Testing

## Dropdown Keys - DO NOT DELETE
KEY DROPDOWNS - DO NOT DELETE
| PRIORITY KEY | STATUS KEY
| High | In Progress
| Medium | Ready to Start
| Low | Complete
On Hold
Testing