## Daily Scrum Meeting
Soluciones Móviles II - DAILY SCRUM STAND UP MEETING
GROUP NAME |  | WEEK START dates below will auto populate | Sprint |  | SUPERVISOR
Control de Acceso Universitario |  | 2025-09-07 | 2 |  | Dr. Ing. Oscar Jimenez
URL tablero |  | https://github.com/orgs/Sistema-de-control-de-acceso/projects/8
URL github |  | https://github.com/Sistema-de-control-de-acceso/MovilesII.git
MON | 2025-09-08
NO. | ASSIGNED TO | PRIORITIES | PRIORITY LEVEL | PROGRESS | PROGRESS STATUS | PROBLEMS AND COMMENTS
1 | Angel Hernandez | Registrar guardias | High | Form design started | Ready to Start | Admin panel from Sprint 1 ready
2 | Angel Hernandez | Activar/desactivar guardias | Medium | Planning toggle system | Ready to Start | Depends on guard registration
3 | Cesar Chavez | Asignar puntos de control | High | Catalog structure design | Ready to Start | Need to define control points first
4 | Sebastian Arce | Modificar datos guardias | Medium | Edit form planning | Ready to Start | History tracking requirements defined
5 | Cesar Chavez | Sincronización datos estudiantes | High | Sync algorithm design | In Progress | Building on stable BD connection
6 | Sebastian Arce | Asociar ID con estudiante | High | Mapping structure defined | Ready to Start | NFC ID reading from Sprint 1 working
7 | Angel Hernandez | Mostrar detecciones tiempo real | Medium | UI mockup created | Ready to Start | Real-time updates architecture needed
8 | Cesar Chavez | Múltiples detecciones | High | Queue system planning | Ready to Start | Complex concurrency handling required
9 | Sebastian Arce | Validar ID pulsera | Medium | Validation logic started | In Progress | Bracelet database schema created
10 | Angel Hernandez | Verificar estado activo | Medium | Status check integration | Ready to Start | Uses existing student status queries
11 | Juan Luna | Mostrar datos estudiante | Medium | Display format defined | Ready to Start | Photo integration pending decision
12 | Sebastian Arce | Autorización manual | High | Button interface design | Ready to Start | Final control before access grant
13 | Juan Luna | Registrar decisión timestamp | Medium | Timestamp system planning | Ready to Start | Audit trail requirements defined
14 | Juan Luna | Registrar accesos | High | Database schema design | In Progress | Core logging functionality
15 | Juan Luna | Guardar fecha, hora, datos | Medium | Data persistence planning | Ready to Start | Complete event data storage
TUES | 2025-09-09
NO. | ASSIGNED TO | PRIORITIES | PRIORITY LEVEL | PROGRESS | PROGRESS STATUS | PROBLEMS AND COMMENTS
1 | Angel Hernandez | Registrar guardias | High | Form validation 60% complete | In Progress | Credential generation system working
2 | Angel Hernandez | Activar/desactivar guardias | Medium | Toggle functionality implemented | In Progress | User notification system 40% done
3 | Cesar Chavez | Asignar puntos de control | High | Control points catalog 70% done | In Progress | Multiple assignment logic implemented
4 | Sebastian Arce | Modificar datos guardias | Medium | Edit form 80% complete | In Progress | History tracking working properly
5 | Cesar Chavez | Sincronización datos estudiantes | High | Scheduled sync working | Testing | Change detection algorithm tested
6 | Sebastian Arce | Asociar ID con estudiante | High | Mapping validation 90% done | In Progress | Handling unregistered IDs properly
7 | Angel Hernandez | Mostrar detecciones tiempo real | Medium | Real-time list 50% complete | In Progress | Auto-update mechanism working
8 | Cesar Chavez | Múltiples detecciones | High | Queue processing implemented | In Progress | Sequential processing 70% done
9 | Sebastian Arce | Validar ID pulsera | Medium | DB validation working | Testing | Invalid ID handling tested
10 | Angel Hernandez | Verificar estado activo | Medium | Status validation complete | Complete | Visual indicators working perfectly
11 | Juan Luna | Mostrar datos estudiante | Medium | Display format implemented | In Progress | Photo integration still pending
12 | Sebastian Arce | Autorización manual | High | Button interface completed | Testing | Visual confirmation working
13 | Juan Luna | Registrar decisión timestamp | Medium | Timestamp precision implemented | In Progress | Guard ID tracking added
14 | Juan Luna | Registrar accesos | High | Database schema finalized | Testing | All access data fields captured
15 | Juan Luna | Guardar fecha, hora, datos | Medium | Persistence layer complete | Testing | Integrity constraints validated
WED | 2025-09-10
NO. | ASSIGNED TO | PRIORITIES | PRIORITY LEVEL | PROGRESS | PROGRESS STATUS | PROBLEMS AND COMMENTS
1 | Angel Hernandez | Registrar guardias | High | All validations working | Complete | Guard registration fully functional
2 | Angel Hernandez | Activar/desactivar guardias | Medium | Notification system complete | Complete | Access blocking working properly
3 | Cesar Chavez | Asignar puntos de control | High | Assignment visualization done | Testing | Testing multiple point assignments
4 | Sebastian Arce | Modificar datos guardias | Medium | History tracking tested | Complete | Change validation working perfectly
5 | Cesar Chavez | Sincronización datos estudiantes | High | Log system implemented | Complete | Automatic sync working reliably
6 | Sebastian Arce | Asociar ID con estudiante | High | Error handling complete | Complete | Association validation robust
7 | Angel Hernandez | Mostrar detecciones tiempo real | Medium | Status indicators added | Testing | Testing real-time update performance
8 | Cesar Chavez | Múltiples detecciones | High | Time prioritization added | Testing | Testing concurrent detection handling
9 | Sebastian Arce | Validar ID pulsera | Medium | All edge cases handled | Complete | ID validation system reliable
10 | Angel Hernandez | Verificar estado activo | Medium | Integration tested | Complete | Status verification optimized
11 | Juan Luna | Mostrar datos estudiante | Medium | Photo integration resolved | Testing | Clear data display achieved
12 | Sebastian Arce | Autorización manual | High | Decision logging added | Complete | Manual control fully functional
13 | Juan Luna | Registrar decisión timestamp | Medium | BD persistence tested | Complete | Audit trail complete and reliable
14 | Juan Luna | Registrar accesos | High | All test cases passed | Complete | Access logging system operational
15 | Juan Luna | Guardar fecha, hora, datos | Medium | Backup system validated | Complete | Data persistence fully reliable
THU | 2025-09-11
NO. | ASSIGNED TO | PRIORITIES | PRIORITY LEVEL | PROGRESS | PROGRESS STATUS | PROBLEMS AND COMMENTS
1 - 15 | All Team | Sprint 2 Integration Testing | High | Form design started | Testing | Testing complete guard management flow
3 | Cesar Chavez | Asignar puntos de control | High | Planning toggle system | Complete | Point assignment system working
7 | Angel Hernandez | Mostrar detecciones tiempo real | Medium | Catalog structure design | Complete | Real-time monitoring operational
8 | Cesar Chavez | Múltiples detecciones | High | Edit form planning | Complete | Multi-detection handling robust
10 | Cesar Chavez | Mostrar datos estudiante | Medium | Sync algorithm design | Complete | Student data display complete
Integration testing of all Sprint 2 features in progress Guard management + NFC processing + Access logging
FRI | 2025-09-12
NO. | ASSIGNED TO | PRIORITIES | PRIORITY LEVEL | PROGRESS | PROGRESS STATUS | PROBLEMS AND COMMENTS
All 15 User Stories completed and integrated • Guard Management System • NFC Bracelet Processing • Access Control & Logging Ready to proceed to Sprint 3

## EXAMPLE Daily Scrum Meeting
Soluciones Móviles II - DAILY SCRUM STAND UP MEETING
GROUP NAME |  | WEEK START dates below will auto populate | Sprint |  | SUPERVISOR
Team Alpha |  | 2024-09-16 | 1 |  | Dr. Ing. Oscar Jimenez
URL tablero |  | https://…
URL github |  | https://…
MON | 2024-09-17
NO. | ASSIGNED TO | PRIORITIES | PRIORITY LEVEL | PROGRESS | PROGRESS STATUS | PROBLEMS AND COMMENTS
1 | Leon W | Project Charter | High | Initial edits started | In Progress | Need input from Team A
2 | Kylie R | Project Charter Revisions | Medium | On hold for initial edits | On Hold
3 | Pete S | Research | Low | Ongoing | In Progress | Document C not currently available
4 | Steve L | Projections | Medium | Drafted | Complete
5 | Allen W | Stakeholders | Medium | Ongoing | In Progress
6 | Malik M | Guidelines | High | Initial edits finalized | Complete
7 | Malik M | Project Initiation | Medium | Not yet started | Ready to Start
8 | Allen W | Scope and Goal Setting | Medium | Ongoing | In Progress
9 | Allen W | Budget | High | Drafted | Complete
10 |  |  | High |  | Testing
TUES | 2024-09-18
NO. | ASSIGNED TO | PRIORITIES | PRIORITY LEVEL | PROGRESS | PROGRESS STATUS | PROBLEMS AND COMMENTS
1 | Leon W | Project Charter | High | Reason 1 | Testing | Description 1
2 | Kylie R | Project Charter Revisions | Medium | Reason 2 | In Progress | Description 2
3 | Pete S | Research | Low | Reason 3 | Ready to Start | Description 3
4 | Steve L | Projections | Medium | Reason 4 | Complete | Description 4
5 | Allen W | Stakeholders | Medium |  | Testing
6 | Malik M | Guidelines | High |  | In Progress
7 | Malik M | Project Initiation | Medium |  | Complete
8 | Allen W | Scope and Goal Setting | Medium |  | Complete
9 | Allen W | Budget | High |  | On Hold
10 |  |  | High |  | Testing
WED | 2024-09-19
NO. | ASSIGNED TO | PRIORITIES | PRIORITY LEVEL | PROGRESS | PROGRESS STATUS | PROBLEMS AND COMMENTS
1 | Leon W | Project Charter | High | Reason 1 | Testing | Description 1
2 | Kylie R | Project Charter Revisions | Medium | Reason 2 | In Progress | Description 2
3 | Pete S | Research | Low | Reason 3 | Ready to Start | Description 3
4 | Steve L | Projections | Medium | Reason 4 | Complete | Description 4
5 | Allen W | Stakeholders | Medium |  | Testing
6 | Malik M | Guidelines | High |  | In Progress
7 | Malik M | Project Initiation | Medium |  | Complete
8 | Allen W | Scope and Goal Setting | Medium |  | Complete
9 | Allen W | Budget | High |  | On Hold
10 |  |  | High |  | Testing
THU | 2024-09-20
NO. | ASSIGNED TO | PRIORITIES | PRIORITY LEVEL | PROGRESS | PROGRESS STATUS | PROBLEMS AND COMMENTS
1 | Leon W | Project Charter | High | Reason 1 | Testing | Description 1
2 | Kylie R | Project Charter Revisions | Medium | Reason 2 | In Progress | Description 2
3 | Pete S | Research | Low | Reason 3 | Ready to Start | Description 3
4 | Steve L | Projections | Medium | Reason 4 | Complete | Description 4
5 | Allen W | Stakeholders | Medium |  | Testing
6 | Malik M | Guidelines | High |  | In Progress
7 | Malik M | Project Initiation | Medium |  | Complete
8 | Allen W | Scope and Goal Setting | Medium |  | Complete
9 | Allen W | Budget | High |  | On Hold
10 |  |  | High |  | Testing
FRI | 2024-09-21
NO. | ASSIGNED TO | PRIORITIES | PRIORITY LEVEL | PROGRESS | PROGRESS STATUS | PROBLEMS AND COMMENTS
1 | Leon W | Project Charter | High | Reason 1 | Testing | Description 1
2 | Kylie R | Project Charter Revisions | Medium | Reason 2 | In Progress | Description 2
3 | Pete S | Research | Low | Reason 3 | Ready to Start | Description 3
4 | Steve L | Projections | Medium | Reason 4 | Complete | Description 4
5 | Allen W | Stakeholders | Medium |  | Testing
6 | Malik M | Guidelines | High |  | In Progress
7 | Malik M | Project Initiation | Medium |  | Complete
8 | Allen W | Scope and Goal Setting | Medium |  | Complete
9 | Allen W | Budget | High |  | On Hold
10 |  |  | High |  | Testing

## Dropdown Keys - DO NOT DELETE
KEY DROPDOWNS - DO NOT DELETE
| PRIORITY KEY | STATUS KEY
| High | In Progress
| Medium | Ready to Start
| Low | Complete
On Hold
Testing
Filled