## Daily Scrum Meeting
Soluciones Móviles II - DAILY SCRUM STAND UP MEETING
GROUP NAME |  | WEEK START dates below will auto populate | Sprint |  | SUPERVISOR
Control de Acceso Universitario |  | 2025-09-14 | 3 |  | Dr. Ing. Oscar Jimenez
URL tablero |  | https://github.com/orgs/Sistema-de-control-de-acceso/projects/8
URL github |  | https://github.com/Sistema-de-control-de-acceso/MovilesII.git
MON | 2025-09-15
NO. | ASSIGNED TO | PRIORITIES | PRIORITY LEVEL | PROGRESS | PROGRESS STATUS | PROBLEMS AND COMMENTS
1 | Cesar Chavez | Reportes actividad guardias | High | Report structure planning | Ready to Start | Using historical data from Sprint 2
2 | Sebastian Arce | Lista estudiantes hoy | Medium | Query design started | Ready to Start | Access logs from Sprint 2 available
3 | Angel Hernandez | Lista estudiantes en campus | High | Entry/exit logic design | Ready to Start | Complex logic for current occupancy
4 | Juan Luna | Buscar estudiante | Medium | Search interface mockup | Ready to Start | Need autocomplete functionality
5 | Sebastian Arce | Historial accesos recientes | Medium | Time filter planning | Ready to Start | 24h/48h filters required
6 | Angel Hernandez | Filtrar por carrera y fechas | High | Filter combination design | In Progress | Complex multi-filter implementation
7 | Juan Luna | Sincronización app-servidor | High | Sync architecture planning | In Progress | Bidirectional sync complexity high
8 | Cesar Chavez | Funcionalidad offline | High | Local cache design | Ready to Start | Critical for guard operations
9 | Juan Luna | Múltiples guardias simultáneos | High | Concurrency analysis started | In Progress | Database locking strategy needed
TUES | 2025-09-16
NO. | ASSIGNED TO | PRIORITIES | PRIORITY LEVEL | PROGRESS | PROGRESS STATUS | PROBLEMS AND COMMENTS
1 | Cesar Chavez | Reportes actividad guardias | High | Activity metrics 60% done | In Progress | PDF export library integration
2 | Sebastian Arce | Lista estudiantes hoy | Medium | Date filtering implemented | In Progress | Chronological ordering working
3 | Angel Hernandez | Lista estudiantes en campus | High | Entry-exit calculation 70% done | In Progress | Counter algorithm implemented
4 | Juan Luna | Buscar estudiante | Medium | Search box with autocomplete | In Progress | Multiple results handling added
5 | Sebastian Arce | Historial accesos recientes | Medium | 24h/48h filters working | Testing | Complete access details displayed
6 | Angel Hernandez | Filtrar por carrera y fechas | High | Date picker implemented | Testing | Career dropdown working properly
7 | Juan Luna | Sincronización app-servidor | High | Conflict resolution 80% done | In Progress | Data versioning system working
8 | Cesar Chavez | Funcionalidad offline | High | Event queue system 50% done | In Progress | Auto-sync on reconnect working
9 | Juan Luna | Múltiples guardias simultáneos | High | Optimistic locking implemented | Testing | Conflict resolution tested
WED | 2025-09-17
NO. | ASSIGNED TO | PRIORITIES | PRIORITY LEVEL | PROGRESS | PROGRESS STATUS | PROBLEMS AND COMMENTS
1 | Cesar Chavez | Reportes actividad guardias | High | PDF generation working | Testing | Performance metrics validated
2 | Sebastian Arce | Lista estudiantes hoy | Medium | Basic filters added | Complete | Daily monitoring fully functiona
3 | Angel Hernandez | Lista estudiantes en campus | High | Real-time counter tested | Complete | Current occupancy accurate
4 | Juan Luna | Buscar estudiante | Medium | Complete data display added | Complete | Search functionality optimized
5 | Sebastian Arce | Historial accesos recientes | Medium | All details validated | Complete | Historical review fully working
6 | Angel Hernandez | Filtrar por carrera y fechas | High | Filter combinations tested | Complete | Advanced filtering operational
7 | Juan Luna | Sincronización app-servidor | High | Data versioning complete | Testing | Bidirectional sync tested
8 | Cesar Chavez | Funcionalidad offline | High | Auto-sync optimized | Testing | Offline resilience validated
9 | Juan Luna | Múltiples guardias simultáneos | High | Scalability tested | Complete | Multi-user operations stable
THU | 2025-09-18
NO. | ASSIGNED TO | PRIORITIES | PRIORITY LEVEL | PROGRESS | PROGRESS STATUS | PROBLEMS AND COMMENTS
1 | Cesar Chavez | Reportes actividad guardias | High | Export functionality validated | Complete | Guard performance reporting ready
7 | Juan Luna | Sincronización app-servidor | High | All edge cases handled | Complete | Sync system fully operational
8 | Cesar Chavez | Funcionalidad offline | High | Stress testing completed | Complete | Offline mode fully functional
Sprint 3 Integration Testing Phase • Query & Reporting System • Mobile App Synchronization • Multi-user Concurrency
FRI | 2025-09-19
NO. | ASSIGNED TO | PRIORITIES | PRIORITY LEVEL | PROGRESS | PROGRESS STATUS | PROBLEMS AND COMMENTS
All 9 User Stories completed and integrated • Advanced Query System • Guard Activity Reports • Mobile-Web Synchronization • Multi-user Concurrent Operations • Offline Functionality Ready to proceed to Sprint 4 (Machine Learning)

## EXAMPLE Daily Scrum Meeting
Soluciones Móviles II - DAILY SCRUM STAND UP MEETING
GROUP NAME |  | WEEK START dates below will auto populate | Sprint |  | SUPERVISOR
Team Alpha |  | 2024-09-16 | 1 |  | Dr. Ing. Oscar Jimenez
URL tablero |  | https://…
URL github |  | https://…
MON | 2024-09-17
NO. | ASSIGNED TO | PRIORITIES | PRIORITY LEVEL | PROGRESS | PROGRESS STATUS | PROBLEMS AND COMMENTS
1 | Leon W | Project Charter | High | Initial edits started | In Progress | Need input from Team A
2 | Kylie R | Project Charter Revisions | Medium | On hold for initial edits | On Hold
3 | Pete S | Research | Low | Ongoing | In Progress | Document C not currently available
4 | Steve L | Projections | Medium | Drafted | Complete
5 | Allen W | Stakeholders | Medium | Ongoing | In Progress
6 | Malik M | Guidelines | High | Initial edits finalized | Complete
7 | Malik M | Project Initiation | Medium | Not yet started | Ready to Start
8 | Allen W | Scope and Goal Setting | Medium | Ongoing | In Progress
9 | Allen W | Budget | High | Drafted | Complete
10 |  |  | High |  | Testing
TUES | 2024-09-18
NO. | ASSIGNED TO | PRIORITIES | PRIORITY LEVEL | PROGRESS | PROGRESS STATUS | PROBLEMS AND COMMENTS
1 | Leon W | Project Charter | High | Reason 1 | Testing | Description 1
2 | Kylie R | Project Charter Revisions | Medium | Reason 2 | In Progress | Description 2
3 | Pete S | Research | Low | Reason 3 | Ready to Start | Description 3
4 | Steve L | Projections | Medium | Reason 4 | Complete | Description 4
5 | Allen W | Stakeholders | Medium |  | Testing
6 | Malik M | Guidelines | High |  | In Progress
7 | Malik M | Project Initiation | Medium |  | Complete
8 | Allen W | Scope and Goal Setting | Medium |  | Complete
9 | Allen W | Budget | High |  | On Hold
10 |  |  | High |  | Testing
WED | 2024-09-19
NO. | ASSIGNED TO | PRIORITIES | PRIORITY LEVEL | PROGRESS | PROGRESS STATUS | PROBLEMS AND COMMENTS
1 | Leon W | Project Charter | High | Reason 1 | Testing | Description 1
2 | Kylie R | Project Charter Revisions | Medium | Reason 2 | In Progress | Description 2
3 | Pete S | Research | Low | Reason 3 | Ready to Start | Description 3
4 | Steve L | Projections | Medium | Reason 4 | Complete | Description 4
5 | Allen W | Stakeholders | Medium |  | Testing
6 | Malik M | Guidelines | High |  | In Progress
7 | Malik M | Project Initiation | Medium |  | Complete
8 | Allen W | Scope and Goal Setting | Medium |  | Complete
9 | Allen W | Budget | High |  | On Hold
10 |  |  | High |  | Testing
THU | 2024-09-20
NO. | ASSIGNED TO | PRIORITIES | PRIORITY LEVEL | PROGRESS | PROGRESS STATUS | PROBLEMS AND COMMENTS
1 | Leon W | Project Charter | High | Reason 1 | Testing | Description 1
2 | Kylie R | Project Charter Revisions | Medium | Reason 2 | In Progress | Description 2
3 | Pete S | Research | Low | Reason 3 | Ready to Start | Description 3
4 | Steve L | Projections | Medium | Reason 4 | Complete | Description 4
5 | Allen W | Stakeholders | Medium |  | Testing
6 | Malik M | Guidelines | High |  | In Progress
7 | Malik M | Project Initiation | Medium |  | Complete
8 | Allen W | Scope and Goal Setting | Medium |  | Complete
9 | Allen W | Budget | High |  | On Hold
10 |  |  | High |  | Testing
FRI | 2024-09-21
NO. | ASSIGNED TO | PRIORITIES | PRIORITY LEVEL | PROGRESS | PROGRESS STATUS | PROBLEMS AND COMMENTS
1 | Leon W | Project Charter | High | Reason 1 | Testing | Description 1
2 | Kylie R | Project Charter Revisions | Medium | Reason 2 | In Progress | Description 2
3 | Pete S | Research | Low | Reason 3 | Ready to Start | Description 3
4 | Steve L | Projections | Medium | Reason 4 | Complete | Description 4
5 | Allen W | Stakeholders | Medium |  | Testing
6 | Malik M | Guidelines | High |  | In Progress
7 | Malik M | Project Initiation | Medium |  | Complete
8 | Allen W | Scope and Goal Setting | Medium |  | Complete
9 | Allen W | Budget | High |  | On Hold
10 |  |  | High |  | Testing

## Dropdown Keys - DO NOT DELETE
KEY DROPDOWNS - DO NOT DELETE
| PRIORITY KEY | STATUS KEY
| High | In Progress
| Medium | Ready to Start
| Low | Complete
On Hold
Testing
Filled