## Daily Scrum Meeting
Soluciones Móviles II - DAILY SCRUM STAND UP MEETING
GROUP NAME |  | WEEK START dates below will auto populate | Sprint |  | SUPERVISOR
Control de Acceso Universitario |  | 2025-09-21 | 4 |  | Dr. Ing. Oscar Jimenez
URL tablero |  | https://github.com/orgs/Sistema-de-control-de-acceso/projects/8
URL github |  | https://github.com/Sistema-de-control-de-acceso/MovilesII.git
MON | 2025-09-22
NO. | ASSIGNED TO | PRIORITIES | PRIORITY LEVEL | PROGRESS | PROGRESS STATUS | PROBLEMS AND COMMENTS
1 | Angel Hernandez | Recopilar datos ML | High | ETL pipeline design started | Ready to Start | 3+ months historical data available
2 | Cesar Chavez | Analizar patrones de flujo | High | Temporal analysis algorithms | Ready to Start | Pattern detection library selected
3 | Juan Luna | Predecir horarios pico | High | Predictive model architecture | Ready to Start | Target: >80% accuracy requirement
4 | Sebastian Arce | Sugerir horarios de buses | High | Optimization algorithm research | Ready to Start | Depends on peak hour predictions
5 | Cesar Chavez | Alertas de congestión | Medium | Alert system design | Ready to Start | Configurable thresholds needed
6 | Angel Hernandez | Regresión lineal | High | Linear regression setup | In Progress | R² validation target: >0.7
7 | Juan Luna | Clustering | High | K-means implementation started | In Progress | Optimal cluster number analysis
8 | Sebastian Arce | Series temporales | High | ARIMA model research | Ready to Start | Seasonality detection required
9 | Cesar Chavez | Entrenar con históricos | High | Dataset preparation 30% done | In Progress | Train/test split configured
10 | Angel Hernandez | Actualización | Medium | Scheduler job planning | Ready to Start | Incremental retraining approach
TUES | 2025-09-23
NO. | ASSIGNED TO | PRIORITIES | PRIORITY LEVEL | PROGRESS | PROGRESS STATUS | PROBLEMS AND COMMENTS
1 | Angel Hernandez | Recopilar datos ML | High | Data cleaning 80% complete | In Progress | ML-ready structure implemented
2 | Cesar Chavez | Analizar patrones de flujo | High | Trend detection 60% done | In Progress | Pattern visualization working
3 | Juan Luna | Predecir horarios pico | High | Model training 50% complete | In Progress | 24h forecast implementation ongoing
4 | Sebastian Arce | Sugerir horarios de buses | High | Optimization logic 40% done | In Progress | Efficiency metrics being calculated
5 | Cesar Chavez | Alertas de congestión | Medium | Alert system 70% complete | In Progress | Multiple notification channels added
6 | Angel Hernandez | Regresión lineal | High | Cross-validation running | Testing | R² score: 0.73 (meeting target)
7 | Juan Luna | Clustering | High | Silhouette validation done | Testing | 5 optimal clusters identified
8 | Sebastian Arce | Series temporales | High | ARIMA model 60% trained | In Progress | Seasonality patterns detected
9 | Cesar Chavez | Entrenar con históricos | High | Training 90% complete | Testing | Validation metrics being computed
10 | Angel Hernandez | Actualización | Medium | Automated job 50% done | In Progress | Performance validation logic added
WED | 2025-09-24
NO. | ASSIGNED TO | PRIORITIES | PRIORITY LEVEL | PROGRESS | PROGRESS STATUS | PROBLEMS AND COMMENTS
1 | Angel Hernandez | Recopilar datos ML | High | ETL pipeline finalized | Complete | Clean data ready for all models
2 | Cesar Chavez | Analizar patrones de flujo | High | Trend visualization complete | Complete | Student flow patterns identified
3 | Juan Luna | Predecir horarios pico | High | Model accuracy: 84% | Testing | Exceeds 80% accuracy requirement
4 | Sebastian Arce | Sugerir horarios de buses | High | Optimization algorithm tested | Testing | Bus schedule suggestions validated
5 | Cesar Chavez | Alertas de congestión | Medium | Threshold configuration done | Complete | Automatic alerts operational
6 | Angel Hernandez | Regresión lineal | High | Error metrics validated | Complete | Linear model production ready
7 | Juan Luna | Clustering | High | Pattern groups documented | Complete | Clustering model operational
8 | Sebastian Arce | Series temporales | High | Forecast precision: 78% | Testing | Exceeds 75% precision target
9 | Cesar Chavez | Entrenar con históricos | High | Model validation complete | Complete | Robust model with 3+ months data
10 | Angel Hernandez | Actualización | Medium | Automated retraining tested | Complete | Weekly update job scheduled
THU | 2025-09-25
NO. | ASSIGNED TO | PRIORITIES | PRIORITY LEVEL | PROGRESS | PROGRESS STATUS | PROBLEMS AND COMMENTS
3 | Juan Luna | Predecir horarios pico | High | 24h forecast | Complete | Peak hour prediction operational
4 | Sebastian Arce | Sugerir horarios buses | High | Final optmization complete | Complete | Bus schedule optimizer ready
8 | Sebastian Arce | Series temporales | High | Production deployment | Complete | Time series forecasting active
Sprint 4 ML Models Integration Testing • Linear Regression Model • K-means Clustering • ARIMA Time Series • Peak Hour Predictor (84% accuracy) • Bus Schedule Optimizer
FRI | 2025-09-26
NO. | ASSIGNED TO | PRIORITIES | PRIORITY LEVEL | PROGRESS | PROGRESS STATUS | PROBLEMS AND COMMENTS
SPRINT 4 COMPLETED SUCCESSFULLY All 10 User Stories completed - ML System Operational Completed ML Features: • ETL Data Pipeline for ML • Student Flow Pattern Analysis • Peak Hour Prediction (84% accuracy) • Bus Schedule Optimization • Congestion Alerts System • Linear Regression Model (R²: 0.73) • K-means Clustering (5 clusters) • ARIMA Time Series (78% precision) • Model Training Pipeline • Automated Weekly Model Updates Ready to proceed to Sprint 5 (Dashboards & Reporting)

## EXAMPLE Daily Scrum Meeting
Soluciones Móviles II - DAILY SCRUM STAND UP MEETING
GROUP NAME |  | WEEK START dates below will auto populate | Sprint |  | SUPERVISOR
Team Alpha |  | 2024-09-16 | 1 |  | Dr. Ing. Oscar Jimenez
URL tablero |  | https://…
URL github |  | https://…
MON | 2024-09-17
NO. | ASSIGNED TO | PRIORITIES | PRIORITY LEVEL | PROGRESS | PROGRESS STATUS | PROBLEMS AND COMMENTS
1 | Leon W | Project Charter | High | Initial edits started | In Progress | Need input from Team A
2 | Kylie R | Project Charter Revisions | Medium | On hold for initial edits | On Hold
3 | Pete S | Research | Low | Ongoing | In Progress | Document C not currently available
4 | Steve L | Projections | Medium | Drafted | Complete
5 | Allen W | Stakeholders | Medium | Ongoing | In Progress
6 | Malik M | Guidelines | High | Initial edits finalized | Complete
7 | Malik M | Project Initiation | Medium | Not yet started | Ready to Start
8 | Allen W | Scope and Goal Setting | Medium | Ongoing | In Progress
9 | Allen W | Budget | High | Drafted | Complete
10 |  |  | High |  | Testing
TUES | 2024-09-18
NO. | ASSIGNED TO | PRIORITIES | PRIORITY LEVEL | PROGRESS | PROGRESS STATUS | PROBLEMS AND COMMENTS
1 | Leon W | Project Charter | High | Reason 1 | Testing | Description 1
2 | Kylie R | Project Charter Revisions | Medium | Reason 2 | In Progress | Description 2
3 | Pete S | Research | Low | Reason 3 | Ready to Start | Description 3
4 | Steve L | Projections | Medium | Reason 4 | Complete | Description 4
5 | Allen W | Stakeholders | Medium |  | Testing
6 | Malik M | Guidelines | High |  | In Progress
7 | Malik M | Project Initiation | Medium |  | Complete
8 | Allen W | Scope and Goal Setting | Medium |  | Complete
9 | Allen W | Budget | High |  | On Hold
10 |  |  | High |  | Testing
WED | 2024-09-19
NO. | ASSIGNED TO | PRIORITIES | PRIORITY LEVEL | PROGRESS | PROGRESS STATUS | PROBLEMS AND COMMENTS
1 | Leon W | Project Charter | High | Reason 1 | Testing | Description 1
2 | Kylie R | Project Charter Revisions | Medium | Reason 2 | In Progress | Description 2
3 | Pete S | Research | Low | Reason 3 | Ready to Start | Description 3
4 | Steve L | Projections | Medium | Reason 4 | Complete | Description 4
5 | Allen W | Stakeholders | Medium |  | Testing
6 | Malik M | Guidelines | High |  | In Progress
7 | Malik M | Project Initiation | Medium |  | Complete
8 | Allen W | Scope and Goal Setting | Medium |  | Complete
9 | Allen W | Budget | High |  | On Hold
10 |  |  | High |  | Testing
THU | 2024-09-20
NO. | ASSIGNED TO | PRIORITIES | PRIORITY LEVEL | PROGRESS | PROGRESS STATUS | PROBLEMS AND COMMENTS
1 | Leon W | Project Charter | High | Reason 1 | Testing | Description 1
2 | Kylie R | Project Charter Revisions | Medium | Reason 2 | In Progress | Description 2
3 | Pete S | Research | Low | Reason 3 | Ready to Start | Description 3
4 | Steve L | Projections | Medium | Reason 4 | Complete | Description 4
5 | Allen W | Stakeholders | Medium |  | Testing
6 | Malik M | Guidelines | High |  | In Progress
7 | Malik M | Project Initiation | Medium |  | Complete
8 | Allen W | Scope and Goal Setting | Medium |  | Complete
9 | Allen W | Budget | High |  | On Hold
10 |  |  | High |  | Testing
FRI | 2024-09-21
NO. | ASSIGNED TO | PRIORITIES | PRIORITY LEVEL | PROGRESS | PROGRESS STATUS | PROBLEMS AND COMMENTS
1 | Leon W | Project Charter | High | Reason 1 | Testing | Description 1
2 | Kylie R | Project Charter Revisions | Medium | Reason 2 | In Progress | Description 2
3 | Pete S | Research | Low | Reason 3 | Ready to Start | Description 3
4 | Steve L | Projections | Medium | Reason 4 | Complete | Description 4
5 | Allen W | Stakeholders | Medium |  | Testing
6 | Malik M | Guidelines | High |  | In Progress
7 | Malik M | Project Initiation | Medium |  | Complete
8 | Allen W | Scope and Goal Setting | Medium |  | Complete
9 | Allen W | Budget | High |  | On Hold
10 |  |  | High |  | Testing

## Dropdown Keys - DO NOT DELETE
KEY DROPDOWNS - DO NOT DELETE
| PRIORITY KEY | STATUS KEY
| High | In Progress
| Medium | Ready to Start
| Low | Complete
On Hold
Testing
Filled