## Daily Scrum Meeting
Soluciones Móviles II - DAILY SCRUM STAND UP MEETING
GROUP NAME |  | WEEK START dates below will auto populate | Sprint |  | SUPERVISOR
Control de Acceso Universitario |  | 2025-09-28 | 5 |  | Dr. Ing. Oscar Jimenez
URL tablero |  | https://github.com/orgs/Sistema-de-control-de-acceso/projects/8
URL github |  | https://github.com/Sistema-de-control-de-acceso/MovilesII.git
MON | 2025-09-29
NO. | ASSIGNED TO | PRIORITIES | PRIORITY LEVEL | PROGRESS | PROGRESS STATUS | PROBLEMS AND COMMENTS
1 | Cesar Chavez | Dashboard general accesos | High | Real-time metrics setup | Ready to Start | Data from previous sprints ready
2 | Sebastian Arce | Gráficos flujo horarios | High | Chart library integration | Ready to Start | Interactive charts with drill-down
3 | Angel Hernandez | Predicciones modelo ML | High | Visualization design started | In Progress | ML predictions from Sprint 4 ready
4 | Juan Luna | Reportes eficiencia buses | Medium | Metrics calculation design | Ready to Start | Before/after comparison needed
TUES | 2025-09-30
NO. | ASSIGNED TO | PRIORITIES | PRIORITY LEVEL | PROGRESS | PROGRESS STATUS | PROBLEMS AND COMMENTS
1 | Cesar Chavez | Dashboard general accesos | High | Interactive graphs 70% done | In Progress | Responsive design implemented
2 | Sebastian Arce | Gráficos flujo horarios | High | Temporal filters 80% complete | In Progress | Day/hour drill-down working
3 | Angel Hernandez | Predicciones modelo ML | High | Confidence intervals added | Testing | Prediction vs real comparison visual
4 | Juan Luna | Reportes eficiencia buses | Medium | Utilization metrics 60% done | In Progress | ROI calculation in progress
WED | 2025-10-01
NO. | ASSIGNED TO | PRIORITIES | PRIORITY LEVEL | PROGRESS | PROGRESS STATUS | PROBLEMS AND COMMENTS
1 | Cesar Chavez | Dashboard general accesos | High | Real-time updates validated | Testing | General dashboard 95% complete
2 | Sebastian Arce | Gráficos flujo horarios | High | All filters implemented | Testing | Flow charts testing phase
3 | Angel Hernandez | Predicciones modelo ML | High | Auto-update implemented | Complete | ML predictions visualization ready
4 | Juan Luna | Reportes eficiencia buses | Medium | ROI calculation completed | Testing | Bus efficiency metrics validated
THU | 2025-10-02
NO. | ASSIGNED TO | PRIORITIES | PRIORITY LEVEL | PROGRESS | PROGRESS STATUS | PROBLEMS AND COMMENTS
3 | Cesar Chavez | Dashboard general accesos | High | Final testing completed | Complete | General dashboard fully operational
4 | Sebastian Arce | Gráficos flujo horarios | High | All filters tested | Complete | Flow visualization complete
8 | Juan Luna | Reportes eficiencia buses | Medium | Final validation done | Complete | Bus efficiency reports operational
Sprint 5 Dashboard Components Integration Testing all visualization modules together
FRI | 2025-10-03
NO. | ASSIGNED TO | PRIORITIES | PRIORITY LEVEL | PROGRESS | PROGRESS STATUS | PROBLEMS AND COMMENTS
SPRINT 5 COMPLETED SUCCESSFULLY All 4 User Stories completed and integrated • General Access Dashboard • Interactive Flow Charts • ML Predictions Visualization • Bus Efficiency Reports Ready to proceed to Sprint 6 (Advanced Reports)

## EXAMPLE Daily Scrum Meeting
Soluciones Móviles II - DAILY SCRUM STAND UP MEETING
GROUP NAME |  | WEEK START dates below will auto populate | Sprint |  | SUPERVISOR
Team Alpha |  | 2024-09-16 | 1 |  | Dr. Ing. Oscar Jimenez
URL tablero |  | https://…
URL github |  | https://…
MON | 2024-09-17
NO. | ASSIGNED TO | PRIORITIES | PRIORITY LEVEL | PROGRESS | PROGRESS STATUS | PROBLEMS AND COMMENTS
1 | Leon W | Project Charter | High | Initial edits started | In Progress | Need input from Team A
2 | Kylie R | Project Charter Revisions | Medium | On hold for initial edits | On Hold
3 | Pete S | Research | Low | Ongoing | In Progress | Document C not currently available
4 | Steve L | Projections | Medium | Drafted | Complete
5 | Allen W | Stakeholders | Medium | Ongoing | In Progress
6 | Malik M | Guidelines | High | Initial edits finalized | Complete
7 | Malik M | Project Initiation | Medium | Not yet started | Ready to Start
8 | Allen W | Scope and Goal Setting | Medium | Ongoing | In Progress
9 | Allen W | Budget | High | Drafted | Complete
10 |  |  | High |  | Testing
TUES | 2024-09-18
NO. | ASSIGNED TO | PRIORITIES | PRIORITY LEVEL | PROGRESS | PROGRESS STATUS | PROBLEMS AND COMMENTS
1 | Leon W | Project Charter | High | Reason 1 | Testing | Description 1
2 | Kylie R | Project Charter Revisions | Medium | Reason 2 | In Progress | Description 2
3 | Pete S | Research | Low | Reason 3 | Ready to Start | Description 3
4 | Steve L | Projections | Medium | Reason 4 | Complete | Description 4
5 | Allen W | Stakeholders | Medium |  | Testing
6 | Malik M | Guidelines | High |  | In Progress
7 | Malik M | Project Initiation | Medium |  | Complete
8 | Allen W | Scope and Goal Setting | Medium |  | Complete
9 | Allen W | Budget | High |  | On Hold
10 |  |  | High |  | Testing
WED | 2024-09-19
NO. | ASSIGNED TO | PRIORITIES | PRIORITY LEVEL | PROGRESS | PROGRESS STATUS | PROBLEMS AND COMMENTS
1 | Leon W | Project Charter | High | Reason 1 | Testing | Description 1
2 | Kylie R | Project Charter Revisions | Medium | Reason 2 | In Progress | Description 2
3 | Pete S | Research | Low | Reason 3 | Ready to Start | Description 3
4 | Steve L | Projections | Medium | Reason 4 | Complete | Description 4
5 | Allen W | Stakeholders | Medium |  | Testing
6 | Malik M | Guidelines | High |  | In Progress
7 | Malik M | Project Initiation | Medium |  | Complete
8 | Allen W | Scope and Goal Setting | Medium |  | Complete
9 | Allen W | Budget | High |  | On Hold
10 |  |  | High |  | Testing
THU | 2024-09-20
NO. | ASSIGNED TO | PRIORITIES | PRIORITY LEVEL | PROGRESS | PROGRESS STATUS | PROBLEMS AND COMMENTS
1 | Leon W | Project Charter | High | Reason 1 | Testing | Description 1
2 | Kylie R | Project Charter Revisions | Medium | Reason 2 | In Progress | Description 2
3 | Pete S | Research | Low | Reason 3 | Ready to Start | Description 3
4 | Steve L | Projections | Medium | Reason 4 | Complete | Description 4
5 | Allen W | Stakeholders | Medium |  | Testing
6 | Malik M | Guidelines | High |  | In Progress
7 | Malik M | Project Initiation | Medium |  | Complete
8 | Allen W | Scope and Goal Setting | Medium |  | Complete
9 | Allen W | Budget | High |  | On Hold
10 |  |  | High |  | Testing
FRI | 2024-09-21
NO. | ASSIGNED TO | PRIORITIES | PRIORITY LEVEL | PROGRESS | PROGRESS STATUS | PROBLEMS AND COMMENTS
1 | Leon W | Project Charter | High | Reason 1 | Testing | Description 1
2 | Kylie R | Project Charter Revisions | Medium | Reason 2 | In Progress | Description 2
3 | Pete S | Research | Low | Reason 3 | Ready to Start | Description 3
4 | Steve L | Projections | Medium | Reason 4 | Complete | Description 4
5 | Allen W | Stakeholders | Medium |  | Testing
6 | Malik M | Guidelines | High |  | In Progress
7 | Malik M | Project Initiation | Medium |  | Complete
8 | Allen W | Scope and Goal Setting | Medium |  | Complete
9 | Allen W | Budget | High |  | On Hold
10 |  |  | High |  | Testing

## Dropdown Keys - DO NOT DELETE
KEY DROPDOWNS - DO NOT DELETE
| PRIORITY KEY | STATUS KEY
| High | In Progress
| Medium | Ready to Start
| Low | Complete
On Hold
Testing
Filled