## Daily Scrum Meeting
Soluciones Móviles II - DAILY SCRUM STAND UP MEETING
GROUP NAME |  | WEEK START dates below will auto populate | Sprint |  | SUPERVISOR
Control de Acceso Universitario |  | 2025-10-12 | 6 |  | Dr. Ing. Oscar Jimenez
URL tablero |  | https://github.com/orgs/Sistema-de-control-de-acceso/projects/8
URL github |  | https://github.com/Sistema-de-control-de-acceso/MovilesII.git
MON | 2025-10-13
NO. | ASSIGNED TO | PRIORITIES | PRIORITY LEVEL | PROGRESS | PROGRESS STATUS | PROBLEMS AND COMMENTS
1 | Sebastian Arce | Exportar reportes PDF/Excel | High | Export libraries setup | Testing | Library issues during export.
2 | Cesar Chavez | Estudiantes más activos | Medium | Ranking algorithm design | Testing | Data formula needs revision.
3 | Sebastian Arce | Horarios pico ML | High | Comparison logic started | In Progress | Debugging validation errors.
4 | Juan Luna | Precisión modelo ML | High | Metrics dashboard planning | In Progress | Metric integration delayed.
TUES | 2025-10-14
NO. | ASSIGNED TO | PRIORITIES | PRIORITY LEVEL | PROGRESS | PROGRESS STATUS | PROBLEMS AND COMMENTS
1 | Sebastian Arce | Exportar reportes PDF/Excel | High | PDF with charts 60% done | Testing | Chart merge errors found.
2 | Cesar Chavez | Estudiantes más activos | Medium | Ranking by access 70% done | In Progress | Real-time update issues.
3 | Sebastian Arce | Horarios pico ML | High | ML accuracy per hour chart | Testing | Dataset unstable; recalibrate.
4 | Juan Luna | Precisión modelo ML | High | Metrics dashboard 70% done | In Progress | UI conflicts causing delay.
WED | 2025-10-15
NO. | ASSIGNED TO | PRIORITIES | PRIORITY LEVEL | PROGRESS | PROGRESS STATUS | PROBLEMS AND COMMENTS
1 | Sebastian Arce | Exportar reportes PDF/Excel | High | Final testing complete | Complete | Minor PDF bugs remain.
2 | Cesar Chavez | Estudiantes más activos | Medium | Final validation done | Complete | Performance issues detected.
Sprint 6 Reports Integration Testing export and analytics features
FRI | 2025-10-17
NO. | ASSIGNED TO | PRIORITIES | PRIORITY LEVEL | PROGRESS | PROGRESS STATUS | PROBLEMS AND COMMENTS
SPRINT 6 COMPLETED SUCCESSFULLY All 4 User Stories completed and integrated • PDF/Excel Export Functionality • Most Active Students Report • ML Peak Hours Validation • ML Model Precision Monitoring Ready to proceed to Sprint 7 (Final Integration)

## EXAMPLE Daily Scrum Meeting
Soluciones Móviles II - DAILY SCRUM STAND UP MEETING
GROUP NAME |  | WEEK START dates below will auto populate | Sprint |  | SUPERVISOR
Team Alpha |  | 2024-09-16 | 1 |  | Dr. Ing. Oscar Jimenez
URL tablero |  | https://…
URL github |  | https://…
MON | 2024-09-17
NO. | ASSIGNED TO | PRIORITIES | PRIORITY LEVEL | PROGRESS | PROGRESS STATUS | PROBLEMS AND COMMENTS
1 | Leon W | Project Charter | High | Initial edits started | In Progress | Need input from Team A
2 | Kylie R | Project Charter Revisions | Medium | On hold for initial edits | On Hold
3 | Pete S | Research | Low | Ongoing | In Progress | Document C not currently available
4 | Steve L | Projections | Medium | Drafted | Complete
5 | Allen W | Stakeholders | Medium | Ongoing | In Progress
6 | Malik M | Guidelines | High | Initial edits finalized | Complete
7 | Malik M | Project Initiation | Medium | Not yet started | Ready to Start
8 | Allen W | Scope and Goal Setting | Medium | Ongoing | In Progress
9 | Allen W | Budget | High | Drafted | Complete
10 |  |  | High |  | Testing
TUES | 2024-09-18
NO. | ASSIGNED TO | PRIORITIES | PRIORITY LEVEL | PROGRESS | PROGRESS STATUS | PROBLEMS AND COMMENTS
1 | Leon W | Project Charter | High | Reason 1 | Testing | Description 1
2 | Kylie R | Project Charter Revisions | Medium | Reason 2 | In Progress | Description 2
3 | Pete S | Research | Low | Reason 3 | Ready to Start | Description 3
4 | Steve L | Projections | Medium | Reason 4 | Complete | Description 4
5 | Allen W | Stakeholders | Medium |  | Testing
6 | Malik M | Guidelines | High |  | In Progress
7 | Malik M | Project Initiation | Medium |  | Complete
8 | Allen W | Scope and Goal Setting | Medium |  | Complete
9 | Allen W | Budget | High |  | On Hold
10 |  |  | High |  | Testing
WED | 2024-09-19
NO. | ASSIGNED TO | PRIORITIES | PRIORITY LEVEL | PROGRESS | PROGRESS STATUS | PROBLEMS AND COMMENTS
1 | Leon W | Project Charter | High | Reason 1 | Testing | Description 1
2 | Kylie R | Project Charter Revisions | Medium | Reason 2 | In Progress | Description 2
3 | Pete S | Research | Low | Reason 3 | Ready to Start | Description 3
4 | Steve L | Projections | Medium | Reason 4 | Complete | Description 4
5 | Allen W | Stakeholders | Medium |  | Testing
6 | Malik M | Guidelines | High |  | In Progress
7 | Malik M | Project Initiation | Medium |  | Complete
8 | Allen W | Scope and Goal Setting | Medium |  | Complete
9 | Allen W | Budget | High |  | On Hold
10 |  |  | High |  | Testing
THU | 2024-09-20
NO. | ASSIGNED TO | PRIORITIES | PRIORITY LEVEL | PROGRESS | PROGRESS STATUS | PROBLEMS AND COMMENTS
1 | Leon W | Project Charter | High | Reason 1 | Testing | Description 1
2 | Kylie R | Project Charter Revisions | Medium | Reason 2 | In Progress | Description 2
3 | Pete S | Research | Low | Reason 3 | Ready to Start | Description 3
4 | Steve L | Projections | Medium | Reason 4 | Complete | Description 4
5 | Allen W | Stakeholders | Medium |  | Testing
6 | Malik M | Guidelines | High |  | In Progress
7 | Malik M | Project Initiation | Medium |  | Complete
8 | Allen W | Scope and Goal Setting | Medium |  | Complete
9 | Allen W | Budget | High |  | On Hold
10 |  |  | High |  | Testing
FRI | 2024-09-21
NO. | ASSIGNED TO | PRIORITIES | PRIORITY LEVEL | PROGRESS | PROGRESS STATUS | PROBLEMS AND COMMENTS
1 | Leon W | Project Charter | High | Reason 1 | Testing | Description 1
2 | Kylie R | Project Charter Revisions | Medium | Reason 2 | In Progress | Description 2
3 | Pete S | Research | Low | Reason 3 | Ready to Start | Description 3
4 | Steve L | Projections | Medium | Reason 4 | Complete | Description 4
5 | Allen W | Stakeholders | Medium |  | Testing
6 | Malik M | Guidelines | High |  | In Progress
7 | Malik M | Project Initiation | Medium |  | Complete
8 | Allen W | Scope and Goal Setting | Medium |  | Complete
9 | Allen W | Budget | High |  | On Hold
10 |  |  | High |  | Testing

## Dropdown Keys - DO NOT DELETE
KEY DROPDOWNS - DO NOT DELETE
| PRIORITY KEY | STATUS KEY
| High | In Progress
| Medium | Ready to Start
| Low | Complete
On Hold
Testing
Filled