## Daily Scrum Meeting
Soluciones Móviles II - DAILY SCRUM STAND UP MEETING
GROUP NAME |  | WEEK START dates below will auto populate | Sprint |  | SUPERVISOR
Control de Acceso Universitario |  | 2025-10-14 | 7 |  | Dr. Ing. Oscar Jimenez
URL tablero |  | https://github.com/orgs/Sistema-de-control-de-acceso/projects/8
URL github |  | https://github.com/Sistema-de-control-de-acceso/MovilesII.git
MON | 2025-10-15
NO. | ASSIGNED TO | PRIORITIES | PRIORITY LEVEL | PROGRESS | PROGRESS STATUS | PROBLEMS AND COMMENTS
1 | Cesar Chavez | Uso buses sugerido vs real | High | Comparative report design | Ready to Start | Adoption metrics tracking needed
2 | Sebastian Arce | Comparativo antes/después | High | ROI calculation framework | In Progress | Cost-benefit analysis started
3 | Juan Luna | Web y app mismo servidor | High | Unified API verification | In Progress | Endpoint compatibility testing
4 | Angel Hernandez | Actualizaciones tiempo real | High | WebSocket implementation | In Progress | Target latency: <2s
TUES | 2025-10-16
NO. | ASSIGNED TO | PRIORITIES | PRIORITY LEVEL | PROGRESS | PROGRESS STATUS | PROBLEMS AND COMMENTS
1 | Cesar Chavez | Uso buses sugerido vs real | High | Comparative charts 80% done | In Progress | Impact measurement visualized
2 | Sebastian Arce | Comparativo antes/después | High | Pre/post KPIs calculated | In Progress | Cost-benefit analysis 70% done
3 | Juan Luna | Web y app mismo servidor | High | API unification tested | Testing | Same BD, compatible endpoints
4 | Angel Hernandez | Actualizaciones tiempo real | High | Push notifications working | Testing | Latency: 1.2s (meets <2s target)
WED | 2025-10-17
NO. | ASSIGNED TO | PRIORITIES | PRIORITY LEVEL | PROGRESS | PROGRESS STATUS | PROBLEMS AND COMMENTS
1 | Cesar Chavez | Uso buses sugerido vs real | High | Impact measured and reported | Complete | Bus adoption report complete
2 | Sebastian Arce | Comparativo antes/después | High | ROI analysis complete | Testing | Cost-benefit validated, ROI positive
3 | Juan Luna | Web y app mismo servidor | High | Data consistency validated | Complete | Unified backend fully operational
4 | Angel Hernandez | Actualizaciones tiempo real | High | All platforms synchronized | Complete | Real-time sync working perfectly
THU | 2025-10-18
NO. | ASSIGNED TO | PRIORITIES | PRIORITY LEVEL | PROGRESS | PROGRESS STATUS | PROBLEMS AND COMMENTS
2 | Sebastian Arce | Comparativo antes/después | High | Final ROI report approved | Complete | Project ROI demonstration ready
FINAL SYSTEM INTEGRATION TESTING Complete End-to-End System Validation Testing All Modules: • Authentication & Authorization System • Guard Management System • NFC Access Control • Student Database Integration • Access Logging & History • Advanced Query System • Mobile-Web Synchronization • Machine Learning Models • Dashboards & Reporting • Real-time Updates • Offline Functionality • ROI Analysis
FRI | 2025-10-19
NO. | ASSIGNED TO | PRIORITIES | PRIORITY LEVEL | PROGRESS | PROGRESS STATUS | PROBLEMS AND COMMENTS
SPRINT 7 COMPLETED - PROJECT FINISHED! Sprint 7 Deliverables (4 User Stories): • Suggested vs Real Bus Usage Report • Before/After Comparative Analysis with ROI • Unified Web-App Backend • Real-time Updates System (Latency: 1.2s)
COMPLETE PROJECT SUMMARY Total: 60 User Stories Completed across 7 Sprints Sprint 1: 11 stories - Authentication, Roles, NFC Detection, DB Integration Sprint 2: 15 stories - Guard Management, Bracelet Processing, Access Logging Sprint 3: 9 stories - Advanced Queries, Reports, Sync, Multi-user Sprint 4: 10 stories - Complete ML/AI System (84% Prediction Accuracy) Sprint 5: 4 stories - Dashboards & ML Visualization Sprint 6: 4 stories - Advanced Reports & Export Functionality Sprint 7: 4 stories - Final Integration & ROI Analysis System Status: PRODUCTION READY All Quality Targets: MET OR EXCEEDED ROI: POSITIVE - Cost-Benefit Analysis Complete

## EXAMPLE Daily Scrum Meeting
Soluciones Móviles II - DAILY SCRUM STAND UP MEETING
GROUP NAME |  | WEEK START dates below will auto populate | Sprint |  | SUPERVISOR
Team Alpha |  | 2024-09-16 | 1 |  | Dr. Ing. Oscar Jimenez
URL tablero |  | https://…
URL github |  | https://…
MON | 2024-09-17
NO. | ASSIGNED TO | PRIORITIES | PRIORITY LEVEL | PROGRESS | PROGRESS STATUS | PROBLEMS AND COMMENTS
1 | Leon W | Project Charter | High | Initial edits started | In Progress | Need input from Team A
2 | Kylie R | Project Charter Revisions | Medium | On hold for initial edits | On Hold
3 | Pete S | Research | Low | Ongoing | In Progress | Document C not currently available
4 | Steve L | Projections | Medium | Drafted | Complete
5 | Allen W | Stakeholders | Medium | Ongoing | In Progress
6 | Malik M | Guidelines | High | Initial edits finalized | Complete
7 | Malik M | Project Initiation | Medium | Not yet started | Ready to Start
8 | Allen W | Scope and Goal Setting | Medium | Ongoing | In Progress
9 | Allen W | Budget | High | Drafted | Complete
10 |  |  | High |  | Testing
TUES | 2024-09-18
NO. | ASSIGNED TO | PRIORITIES | PRIORITY LEVEL | PROGRESS | PROGRESS STATUS | PROBLEMS AND COMMENTS
1 | Leon W | Project Charter | High | Reason 1 | Testing | Description 1
2 | Kylie R | Project Charter Revisions | Medium | Reason 2 | In Progress | Description 2
3 | Pete S | Research | Low | Reason 3 | Ready to Start | Description 3
4 | Steve L | Projections | Medium | Reason 4 | Complete | Description 4
5 | Allen W | Stakeholders | Medium |  | Testing
6 | Malik M | Guidelines | High |  | In Progress
7 | Malik M | Project Initiation | Medium |  | Complete
8 | Allen W | Scope and Goal Setting | Medium |  | Complete
9 | Allen W | Budget | High |  | On Hold
10 |  |  | High |  | Testing
WED | 2024-09-19
NO. | ASSIGNED TO | PRIORITIES | PRIORITY LEVEL | PROGRESS | PROGRESS STATUS | PROBLEMS AND COMMENTS
1 | Leon W | Project Charter | High | Reason 1 | Testing | Description 1
2 | Kylie R | Project Charter Revisions | Medium | Reason 2 | In Progress | Description 2
3 | Pete S | Research | Low | Reason 3 | Ready to Start | Description 3
4 | Steve L | Projections | Medium | Reason 4 | Complete | Description 4
5 | Allen W | Stakeholders | Medium |  | Testing
6 | Malik M | Guidelines | High |  | In Progress
7 | Malik M | Project Initiation | Medium |  | Complete
8 | Allen W | Scope and Goal Setting | Medium |  | Complete
9 | Allen W | Budget | High |  | On Hold
10 |  |  | High |  | Testing
THU | 2024-09-20
NO. | ASSIGNED TO | PRIORITIES | PRIORITY LEVEL | PROGRESS | PROGRESS STATUS | PROBLEMS AND COMMENTS
1 | Leon W | Project Charter | High | Reason 1 | Testing | Description 1
2 | Kylie R | Project Charter Revisions | Medium | Reason 2 | In Progress | Description 2
3 | Pete S | Research | Low | Reason 3 | Ready to Start | Description 3
4 | Steve L | Projections | Medium | Reason 4 | Complete | Description 4
5 | Allen W | Stakeholders | Medium |  | Testing
6 | Malik M | Guidelines | High |  | In Progress
7 | Malik M | Project Initiation | Medium |  | Complete
8 | Allen W | Scope and Goal Setting | Medium |  | Complete
9 | Allen W | Budget | High |  | On Hold
10 |  |  | High |  | Testing
FRI | 2024-09-21
NO. | ASSIGNED TO | PRIORITIES | PRIORITY LEVEL | PROGRESS | PROGRESS STATUS | PROBLEMS AND COMMENTS
1 | Leon W | Project Charter | High | Reason 1 | Testing | Description 1
2 | Kylie R | Project Charter Revisions | Medium | Reason 2 | In Progress | Description 2
3 | Pete S | Research | Low | Reason 3 | Ready to Start | Description 3
4 | Steve L | Projections | Medium | Reason 4 | Complete | Description 4
5 | Allen W | Stakeholders | Medium |  | Testing
6 | Malik M | Guidelines | High |  | In Progress
7 | Malik M | Project Initiation | Medium |  | Complete
8 | Allen W | Scope and Goal Setting | Medium |  | Complete
9 | Allen W | Budget | High |  | On Hold
10 |  |  | High |  | Testing

## Dropdown Keys - DO NOT DELETE
KEY DROPDOWNS - DO NOT DELETE
| PRIORITY KEY | STATUS KEY
| High | In Progress
| Medium | Ready to Start
| Low | Complete
On Hold
Testing
Filled